## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | MovieMGMT:001 | Design Documentation for Backend application | Govind | Shashwat | Average |  |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 22 hrs | Design is fullfilled agaist Business requirement
| 2 | Standard document |  | MovieMGMT:002 | Test plan | Govind | Shashwat | Simple |  |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 5 hrs | Check the test case is fullfiled with user accepance criteria document
2 | 3 | Standard document | High | MovieMGMT:003 | Bootstrapping the project | Govind | Shashwat | Simple |  |  |  | Non-Functional |  |  |  |  | 5 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | 4 | Work session | High | MovieMGMT:004 | Creating Entity Class Populating the data | Govind | Shashwat | Simple |  |  |  | Functional |  |  |  |  | 8 hrs | Checking against the Table design in RD
4 | 5 | Work session | High | MovieMGMT:005 | displaying avaibale active movies in backend. | Govind | Shashwat | Average |  |  |  | Functional |  |  |  |  | 4 hrs | TC_Service_01,TC_DAO_01, TC_UI_01
5 | 6 | Work session | High | MovieMGMT:006 | getting shows and screens based on movie id | Govind | Shashwat | Complex |  |  |  | Functional |  |  |  |  | 16hrs | TC_Service_02,TC_DAO_02, TC_UI_03
6 | 7 | Work session | High | MovieMGMT:007 | search movies based on user input | Govind | Shashwat | Complex | [8 empty] | 9 hrs
7 | 8 | Work session | High | MovieMGMT:008 | display booking details | Govind | Shashwat | Complex | [8 empty] | 9 hrs
8 | 9 | Work session | High | MovieMGMT:009 | cancelling booking | Govind | Shashwat | Average | [8 empty] | 5 hrs
9 | 10 | Work session | High | MovieMGMT:010 | search shows using screen name, date, movie id | Govind | Shashwat | Complex | [8 empty] | 9 hrs
10 | 11 | [15 empty] | 5 hrs
11 | 12
12 | 13
13 | 14
14 | 15
Sprint 2 | Sprint 2
15 | 16 | Standard document | High | MovieMGMT:011 | Design Documentation fo Angular application and wireframe | Govind | Shashwat | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional
| 17 |  |  | MovieMGMT:012 | Test plan
16 | 18 |  |  | MovieMGMT:013 | Bootstrapping the project
17 | 19 |  |  | MovieMGMT:014 | designing template and check routing
18 | 20 |  |  | MovieMGMT:015 | creating display movies component
19 | 21 |  |  | MovieMGMT:016 | creating display shows and display screens components
20 | 22 |  |  | MovieMGMT:017 | component for search functionalities
21 | 23 |  |  | MovieMGMT:018 | design component for displaying booking details
22 | 24 |  |  | MovieMGMT:019 | Create a booking movie and cancelling component
23 | 25
Sprint 3 | Sprint 3
1 | 2 | Standard document | High | MovieMGMT: 020 | Integrate spring boot, backend files of all team members.
2 | 2 | Standard document | High | MovieMGMT: 021 | Check functioning of integrated backend in postman.
3 | 3 | Standard document | High | MovieMGMT: 022 | Integrated all angular components in one unified project
4 | 4 | Standard document | High | MovieMGMT: 023 | Check functioning of integraed project that taked data from web service url geenrated by spring backend.
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.

## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | MovieMGMT:001 | 1 | Entity Class Design | Shashwat | 2020-04-16 | 4 hrs | 2 hrs | Completed | 2
|  | 2 | Table Design | Anand | 2020-04-16 | 2 hrs | 2 hrs | Completed | 1.5
|  | 3 | Application Architecture | Gaurav | 2020-04-16 | 1 hrs | 1 Hrs | Completed | 1
|  | 4 | Use case diagram | Shashwat | 2020-04-16 | 2 hrs | 1 hrs | Completed | 1
|  | 5 | Sequence Diagram | Chaitanya kumar | 2020-04-16 | 4 hrs | 2 hrs | Completed | 2
|  | 6 | Each use case detail description | Shashwat | 2020-04-16 | 4 hrs | 1 hrs | Completed | 3
|  | 7 | Class Layer diagram | Anand | 2020-04-16 | 1 hrs | 1 hrs | Completed | 1
|  | 8 | Class Diagram | Gaurav | 2020-04-16 | 2 hrs | 1 hrs | Completed | 1
|  | 9 | Webservice URL Details | Madan | 2020-04-16 | 2 hrs | 1 hrs | Completed | 4
2 | MovieMGMT:002 | 1 | Test plan for dao, | Gaurav | 2020-04-16 | 2 hrs | 1 hrs | Completed | 1.5
|  | 2 | Test plan for service | Chaitanya | 2020-04-16 | 2 hrs | 1 hrs | Completed | 2
|  | 3 | Test plan for webservice methods | Shashwat | 2020-04-16 | 1 hrs | 1 hrs | Completed | 0.5
3 | MovieMGMT:003 | 1 | Creating a Spring boot starter project | Shashwat | 2020-04-17 | 2 hrs | 0.5 hrs | Completed | 0.5
|  | 2 | Adding dependencies in Pom.xml and initializing it | Shashwat | 2020-04-17 | 1 hrs | 0.5 hrs | Completed | 0.5
|  | 3 | Adding server, jpa and logging properties in application.properties | Shashwat | 2020-04-17 | 1 hrs | 0.5 hrs | Completed | 0.5
4 | MovieMGMT:004 | 1 | Entity Class Design | Anand | 2020-04-17 | 2 hrs | 1 hrs | Completed | 1
|  | 2 | Check tables are poulated in DB | Anand | 2020-04-17 | .5 hrs | .5 hrs | Completed | 0.5
|  | 3 | Populate the Data | Anand | 2020-04-17 | 2 hrs | 1 hrs | Completed | 3
5 | MovieMGMT:005 | 1 | Write a JPQL query to retrieve the movies into DAO layer | Madan | 2020-04-17 | 2 hrs | 1 hrs | Completed | 6
|  | 2 | service method invoke the Dao and get the list. | Madan | 2020-04-17 | 2 hrs | 1 hrs | Completed | 6
|  | 3 | RestController method get the movie details and push the list into a GetMapping | Madan | 2020-04-17 | 2 hrs | 1 hrs | Completed | 6
6 | MovieMGMT:006 | 1 | Write a JPQL query to retrieve the shows and screens by taking movie id as input into DAO layer | Gaurav | 2020-04-17 | 3 hrs | 1 hrs | Completed | 3
|  | 2 | service method invoke the Dao and get the shows and screens. | Gaurav | 2020-04-17 | 2 hrs | 1 hrs | Completed | 2
|  | 3 | Throw exception ShowException if show does not exist for the movie. | Gaurav | 2020-04-18 | 4 hrs | 1 hrs | Completed | 3
|  | 4 | RestController method get the movie details and push the list into a GetMapping | Gaurav | 2020-04-17 | 1 hrs | 1 hrs | Completed | 1
c | MovieMGMT:007 | 1 | Write a JPQL query to retrieve the movies by taking name/director/genre as input into DAO layer | Shashwat | 2020-04-17 | 3 hrs | 2 hrs | Completed | 2
|  | 2 | service method invoke the Dao and get the movies. | Shashwat | 2020-04-17 | 2 hrs | 1 hrs | Completed | 2
|  | 3 | Throw exception MovieNotFoundException if show does not exist for the movie. | Shashwat | 2020-04-17 | 2 hrs | 2 hrs | Completed | 1
|  | 4 | RestController method get the movie details and push the list into a GetMapping | Shashwat | 2020-04-17 | 3 hrs | 2 hrs | Completed | 2
8 | MovieMGMT:008 | 1 | Write a JPQL query to retrieve the booking details of user using contact number. | Anand | 2020-04-17 | 2 hrs | 1hrs | Completed | 2
|  | 2 | Service Method invoke the Dao and get the booking Details. | Anand | 2020-04-17 | 3 hrs | 2 hrs | Completed | 2
|  | 3 | Throw exception BookingException if details does not exist for the given Contact number. | Anand | 2020-04-17 | 2 hrs | 2 hrs | Completed | 1
|  | 4 | RestController method get the booking details and push the list into a GetMapping. | Anand | 2020-04-17 | 3 hrs | 2 hrs | Completed | 2
9 | MovieMGMT:009 | 1 | Write a JPQL query to cancel booking DAO layer | Chaitanya | 2020-04-18 | 3 hrs | 1 hrs | Completed | 2
|  | 2 | service method invoke the Dao and cancells the movie | Chaitanya | 2020-04-18 | 3 hrs | 1 hrs | Completed | 2
|  | 3 | Throw exception BookingException if booking does not exist for the movie. | Chaitanya | 2020-04-18 | 3 hrs | 1 hrs | Completed | 2
c | MovieMGMT:0010 | 1 | Write a JPQL query to search the movies by taking show name movie id as input into DAO layer | Shashwat | 2020-04-18 | 4 | 2 hrs | Completed | 2.5
|  | 2 | service method invoke the Dao and get the movies. | Shashwat | 2020-04-18 | 1 | 1 hrs | Completed | 2
|  | 3 | Throw exception ShowNotFoundException if show does not exist for the movie. | Shashwat | 2020-04-18 | 3 | 2 hrs | Completed | 0.5
|  | 4 | RestController method get the movie details and push the list into a GetMapping | Shashwat | 2020-04-18 | 2 | 2 hrs | Completed | 2
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| MovieMGMT:011 | 1 | Wireframes and story boarding for each task |  | 2020-04-24 | 4 hrs | 2.5 hrs | Complete | 2
|  | 2 | Routing Url List | Shashwat | 2020-04-24 | 1 hrs | 1 hrs | Complete
|  | 3 | Data classes details |  | 2020-04-24 | 3 hrs | 2 hrs | Complete | 2
|  | 4 | Angular service |  | 2020-04-24 | 4 hrs | 2 hrs | Complete | 3
|  | 5 | Components details |  | 2020-04-24 | 4 hrs | 2 hrs | Complete | 2
| MovieMGMT:012 | 1 | Test Plan for Components |  | 2020-04-24 | 4 hrs | 2.5 hrs | Complete | 2
|  | 2 | Test Plan for Service |  | 2020-04-24 | 3 hrs | 2 hrs | Complete | 2
| MovieMGMT:013 | 1 | Creating an Angular Project |  | 2020-04-24 | 2 hrs | 2 hrs | Complete | 1.5
|  | 2 | Adding Routing URL's in App Routing Module | Shashwat | 2020-04-24 | 1 hrs | 1 hrs | Complete | 1.5
|  | 3 | Creating Models to model the data. |  | 2020-04-24 | 1 hrs | 1 hrs | Complete | 1
| MovieMGMT:014 | 1 | Designing menu in template. |  | 2020-04-25 | 2 hrs | 2 hrs | Complete | 2
|  | 2 | Checking all Routings are working fine or not. |  | 2020-04-25 | 1 hrs | 1 hrs | Complete | 1
|  | 3 | Verifying all links are displaying desired interface. |  | 2020-04-25 | 1 hrs | 1 hrs | Complete | 1
| MovieMGMT:015 | 1 | Design a form that captures all the Movies. | Madhan | 2020-04-25 | 3 hrs | 2 hrs | Complete | 2
|  | 2 | Component takes the movie details and sends it to Angular Service. | Madhan | 2020-04-25 | 2 hrs | 2 hrs | Complete | 1.5
|  | 3 | Angular Service makes a call to the webservice of Spring and retrieves the movie list. | Madhan | 2020-04-25 | 2 hrs | 2 hrs | Complete | 2
|  | 4 | Design an interface to display generated result or error response sent by the server. | Madhan | 2020-04-25 | 2 hrs | 1.5 hrs | Complete | 2
| MovieMGMT:016 | 1 | Design a form that captures all the Shows. | Gaurav | 2020-04-25 | 3 hrs | 2 hrs | Complete | 2
|  | 2 | Angular Component then takes the shows details and sends it to Angular Service. | Gaurav | 2020-04-25 | 2 hrs | 1.5 hrs | Complete | 2
|  | 3 | Angular Service then makes a call to the webservice of Spring and retrieves the show list. | Gaurav | 2020-04-25 | 2 hrs | 2 hrs | Complete | 2
|  | 4 | If the shows are present then is displayed on interface with datails or it shows the error message. | Gaurav | 2020-04-25 | 2 hrs | 1.5 hrs | Complete | 1
| MovieMGMT:017 | 1 | Design a form to search for movies by taking name/director/genre as input in search box. | Shashwat | 2020-04-25 | 3 hrs | 2 hrs | Complete | 2
|  | 2 | The Angular Component then sends the input details to the Angular Service. | Shashwat | 2020-04-25 | 2 hrs | 2 hrs | Complete | 2
|  | 3 | Angular Service then makes a call to the webservice of Spring and retrieves the movies list. | Shashwat | 2020-04-25 | 2 hrs | 1.5 | Complete | 2
|  | 4 | If the input detail matches with a movie from the list then the movie with its details are displayed on the interface.If it does not match, then it generates a error message. | Shashwat | 2020-04-25 | 2 hrs | 2 hrs | Complete | 2
| MovieMGMT:018 | 1 | Design a form search for booking details by taking contact number as input in search box. | Anand | 2020-04-25 | 3 hrs | 2 hrs | Complete | 2
|  | 2 | The Angular Component then sends the input detail to the Angular Service. | Anand | 2020-04-25 | 2 hrs | 2 hrs | Complete | 2
|  | 3 | Angular Service the makes a call to the webservice of Spring and retrieves all the booking history for that contact number. | Anand | 2020-04-25 | 2 hrs | 1.5 hrs | Complete | 1.5
|  | 4 | If the Contact number matches with any user then booking history is displayed on the screen or an error message is generated. | Anand | 2020-04-25 | 2 hrs | 1.5 hrs | Complete | 1
| MovieMGMT:019 | 1 | Creating booking movie component and cancelling | Chaitanya | 2020-04-25 | 2 hrs | 3 hrs | Complete | 1
|  | 2 | Creating angular service for the web service url. | Chaitanya | 2020-04-25 | 2 hrs | 3 hrs | Complete | 1
|  | 3 | check if the post request and get if reflected in DB. | Chaitanya | 2020-04-25 | 2 hrs | 3 hrs | Complete | 1
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.