## Product Backlog (Scrum)
Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | Standard document | High | USBanking:001 | Design Documentation for Backend application |  |  | Average | Average |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 23 hrs | Design is fullfilled agaist Business requirement
2 | Standard document |  | USBanking:002 | Test Plan |  |  | Average | Average |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 8 hrs | Check the test case is fullfiled with user accepance criteria document
3 | Standard document |  | USBanking:003 | Bootstrapping the project |  |  | Simple | Average | RD:1 Application SetUp | RD: BankDesinDocument_ver1 | Non-Functional |  |  |  |  | 4 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
4 | Work session |  | USBanking:004 | Entity Class, Table design and Populating the data |  |  | Complex | Average | RD:2 Entity Class Design and RD:3 Table Design | RD: BankDesinDocument_ver2 | non-Functional |  |  |  |  | 8 hrs | Checking against the Table design in RD
5 | Work session |  | USBanking:005 | Add Customer |  |  | Complex | High | RD:4 Adding Customer | RD: BankDesinDocument_ver3 | Functional |  |  |  |  | 8 hrs | TC_Service_01,TC_DAO_01, TC_UI_01
6 | Work session |  | USBanking:006 | Add Account |  |  | Complex | High | RD:5 Adding Account | RD: BankDesinDocument_ver4 | Functional |  |  |  |  | 7 hrs | TC_Service_02,TC_DAO_02, TC_UI_03
7 | Work session |  | USBanking:007 | View Accounts for Customer Id |  |  | Complex | Average | RD:6 Displaying Accounts | RD: BankDesinDocument_ver5 | Functional |  |  |  |  | 12 hrs | TC_Service_01,TC_DAO_01, TC_UI_03
8 | Work session |  | USBanking:008 | Transfer Fund |  |  | Complex | High | RD:7 Transfer Fund | RD: BankDesinDocument_ver6 | Functional |  |  |  |  | 12 hrs | TC_Service_04,TC_DAO_04.TC_UI_04 | .
9 | Work session |  | USBanking:009 | view Transaction for AccountID and view transaction with date range |  |  | Complex | Average | RD:8 View Transactions | RD: BankDesinDocument_ver7 | Functional |  |  |  |  | 12 hrs | TC_Service_05,TC_DAO_05, TC_UI_05 | .
10 | Work session |  | USBanking:010 | Login Module |  |  | Complex | High | RD:9 Login and Logout | RD: BankDesinDocument_ver8 | Functional |  |  |  |  | 8 hrs | TC_Service_06,TC_DAO_06, TC_UI_06 | .
11
12
13
14
Sprint 2
15 | Standard document | High | USBanking:011 | Design Documentation fo Angular application |  |  | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non-Functional |  |  |  |  | 12 hrs
16 | Standard document | High | USBanking:012 | Test Plan |  |  | Complex | Average | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non-Functional |  |  |  |  | 17 hrs
17 | Standard Document | High | USBanking:013 | Bootstrapping angular application |  |  | Complex | High | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non-Functional |  |  |  |  | 2 hrs
18 | Standard document | High | USBanking:013 | Design a home page having standard menus |  |  | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non-Functional |  |  |  |  | 6 hrs
19 | Work Session | High | USBanking:014 | Add Customer |  |  | Complex | High | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Functional |  |  |  |  | 8 hrs
20 | Work Session | High | USBanking:015 | Add Account |  |  | Complex | High |  |  | Functional |  |  |  |  | 8 hrs
21 | Work Session | High | USBanking:016 | View Accounts for Customer Id |  |  | Complex | Average |  |  | Functional |  |  |  |  | 7 hrs
22 | Work Session | High | USBanking:017 | Transfer Fund |  |  | Complex | High |  |  | Functional |  |  |  |  | 8 hrs
23 | Work Session | High | USBanking:018 | view Transaction for AccountID and view transaction with date range |  |  | Complex | Average |  |  | Functional |  |  |  |  | 8 hrs
24 | Work Session | High | USBanking:019 | Login Module |  |  | Complex | High |  |  | Functional |  |  |  |  | 8 hrs
25 | Work Session | High | USBanking:020 | My Profile |  |  | Complex | Average |  |  | Functional |  |  |  |  | 2 hrs
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
Note on A4: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on B4: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on C4: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on D4: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on E4: Brief description of the requirements necessary to fulfill the objective
Note on F4: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on G4: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H4: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on I4: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on J4: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on K4: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on L4: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on M4: Column provides linkage to primary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on N4: Column provides linkage to secondary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on O4: Use column for supporting comments.
Note on P4: Column for defining the agreed upon acceptance criteria
Note on Q4: Description of the condition(s) that indicate the requirement has been satisfied.
Note on R4: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on S4: This column is used to provide supporting information, such as changes to the original requirement.
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.

## Sprint Backlog 1 (Scrum)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| USBanking:001 | 1 | Entity class design | Yogesh | 2020-04-16 | 4 hrs | 2 hrs | Completed | 2.5 hrs
|  | 2 | Table Design | Megha | 2020-04-16 | 2 hrs | 1 hrs | Completed | 2 hrs
|  | 3 | Application Architecture | Shubham | 2020-04-16 | 1 hrs | 0.5 hrs | Completed | 1 hrs
|  | 4 | Use Case diagram | Megha | 2020-04-16 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 5 | Sequence Diagram | Rohita | 2020-04-16 | 4 hrs | 1 hrs | Completed | 3 hrs
|  | 6 | Each use case detail description | Shubham | 2020-04-16 | 4 hrs | 1.5 hrs | Completed | 3 hrs
|  | 7 | Class Layer diagram | Rohita | 2020-04-16 | 1 hrs | 0.5 hrs | Completed | 1 hrs
|  | 8 | Class Diagram | Madhu | 2020-04-16 | 2 hrs | 0.5 hrs | Completed | 2 hrs
|  | 9 | WebService URL details | Madhu | 2020-04-16 | 3 hrs | 1 hrs | Completed | 2 hrs
| USBanking:002 | 1 | Test Plan for dao | Shubham | 2020-04-17 | 2.5 hrs | 0.5 hrs | Completed | 2 hrs
|  | 2 | Test Plan for service | Yogesh | 2020-04-17 | 2.5 hrs | 0.5 hrs | Completed | 2.5 hrs
|  | 3 | Test Plan for webservice method | Megha | 2020-04-17 | 2.5 hrs | 0.5 hrs | Completed | 1.5 hrs
| USBanking:003 | 1 | Creating a Spring boot starter project | Rohita | 2020-04-17 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it | Madhu | 2020-04-17 | 1 hrs | 0.5 hrs | Completed | 0.5 hrs
|  | 3 | Adding server,jpa and logging properties in application.properties | Madhu | 2020-04-17 | 1 hrs | 0.5 hrs | Completed | 0.5 hrs
| USBanking:004 | 1 | Entity Class Design | Yogesh | 2020-04-18 | 2.5 hrs | 0.5 hrs | Completed | 2 hrs
|  | 2 | Check tables are populated in DB | Madhu | 2020-04-18 | 1 hrs | 0.5 hrs | Completed | 0.5 hrs
|  | 3 | Populate Data | Shubmam | 2020-04-18 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
| USBanking:005 | 1 | Write a JPQL query to add the customer entity object and edit the customer details to the persistent context in DAO Layer and Wite a JPQL query to retrive the customer details for an accound in Dao | Madhu | 2020-04-19 | 2 hr | 0.5 hrs | Completed | 2 hrs
|  | 2 | Service method invokes the DAO method and sets the datails of a customer and generating the customerID by considering the instant year,value of month,day of month,Hour, Minute, Second. | Madhu | 2020-04-20 | 2 hrs | 0.5 hrs | Completed | 2hrs
|  | 3 | Service method finds the branch code and sets thedetails of branch in customer details | Madhu | 2020-04-21 | 1 hr | 0.5 hrs | Completed | 1 hr
|  | 4 | Rest controller method post the request from service layer and binds the request body to Dto object. | Madhu | 2020-04-22 | 3 hrs | 0.5 hrs | completed | 2.5 hrs
| USBanking:006 | 1 | Wite a JPQL query to add the Account entity object to the persistent context in DAO Layer | Madhu | 2020-04-19 | 2hrs | 0.5 hrs | Completed | 2hrs
|  | 2 | Service Method Fetches the details of customer according to the customerID. If customer is NULL throws customer not found. | Madhu | 2020-04-20 | 1 hrs | 0.5 hrs | Completed | 1 hrs
|  | 3 | In Case customer is found, Service method invokes the DAO method and sets the account details | Madhu | 2020-04-21 | 2 hrs | 0.5 hrs | completed | 2 hrs
|  | 4 | Rest controller method post the request from service layer and binds the request body to Dto object and returns Account ID. | Madhu | 2020-04-22 | 2hrs | 0.5 hrs | complted | 1.5 hrs
| USBanking:007 | 1 | Write a JPQL query to retrive the List Of Accounts for a CustomerID in DAO Layer. | Yogesh | 2020-04-19 | 3 hrs | 0.5 hrs | Completed | 2 hrs
|  | 2 | Service method invokes the DAO method and gets the list.If the list is empty throw Customer Exception "Invalid Customer". | Yogesh | 2020-04-20 | 3 hrs | 0.5 hrs | Completed | 2.5 hrs
|  | 3 | Service method then Sorts the Account according to Account Name. And returns result to RestController function. | Yogesh | 2020-04-21 | 3 hrs | 0.5 hrs | Completed | 2.5 hrs
|  | 4 | RestController method gets the list of Accounts from service layer and returns it as JSON object to WebService | Yogesh | 2020-04-22 | 3 hrs | 0.5 hrs | Completed | 2 hrs
| USBanking:008 | 1 | Write a method to get all the details of a Account through a unique Account ID. | Rohita | 2020-04-19 | 1 hr | 0.5 hrs | Completed | 1.5 hrs
|  | 2 | Service method invokes the DAO method and get the details of the Payee Account and Beneficiary Account. If both the Accounts are not in the database it will throw Account Exception "Account does not exist". Also if the Payee Account balance is less than the transaction amount, it will throw Balance Exception "Insufficient Balance". Also if the Account is inactive then its throws Transaction Exception. | Rohita | 2020-04-20 | 3 hrs | 0.5 hrs | Completed | 2 hrs
|  | 3 | Service method then transfer funds from account to another and call the method to add the transaction in the transaction List. | Rohita | 2020-04-21 | 3 hrs | 0.5 hrs | Completed | 2 hrs
|  | 4 | Rest controller method binds the request body to the DTO object and throws Balance Exception and Account exception. | Rohita | 2020-04-22 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 5 | Rest controller method post the request from service layer and return it as a JSON object to WebService. | Rohita | 2020-04-22 | 3 hrs | 0.5 hrs | Completed | 2 hrs
| USBanking:009 | 1 | Write a JPQL query to retrive the specified number of transactions for a accountId in DAO Layer. | Megha | 2020-04-19 | 1.5 hrs | 0.5 hrs | Completed | 1 hrs
|  | 2 | Write a JPQL query to retrive the transactions within a given date range for a accountId in DAO Layer. | Megha | 2020-04-19 | 1.5 hrs | 0.5 hrs | Completed | 1 hrs
|  | 3 | Service method invokes the DAO method of retreive a specified number of transactions and gets the list. If the list is empty throw exception "No transactions" and if account Id is invalid throw exception "Invalid accountId" | Megha | 2020-04-20 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 4 | Service method invokes the DAO method of retreive transactions for a given date range and gets the list.If the list is empty throw exception "No Transactions" and if account Id is invalid throw exception "Invalid accountId" | Megha | 2020-04-20 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 5 | Service method then returns the specified no.of transactions as a result to RestController function. | Megha | 2020-04-21 | 2.5 hrs | 0.5 hrs | Completed | 2 hrs
|  | 6 | Service method then returns the transactions in a given date range as a result to RestController function. | Megha | 2020-04-21 | 2.5 hrs | 0.5 hrs | Completed | 1 hrs
|  | 7 | RestController method gets the list of transactions from service layer and returns it as JSON object to WebService. | Megha | 2020-04-22 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 8 | RestController method gets the list of transactions in a date range from service layer and returns it as JSON object toWebService. | Megha | 2020-04-22 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
| USBanking:010 | 1 | Write a method in DAO to get a customer through a unique customer ID. | Shubham | 2020-04-19 | 1 hr | o.5 hr | Completed | 1 hrs
|  | 2 | Write Service method that takes customer ID and password as argument and which validates a customer | Shubham | 2020-04-20 | 1 hr | 0.5 hr | Completed | 1 hrs
|  | 3 | Service method invokes the getCustomer method in DAO which return a customer with the particular customer ID or returns null if no customer with that customer ID exists. | Shubham | 2020-04-20 | 1 hr | 0.5 hrs | Completed | 1 hrs
|  | 4 | If the customer returned by the DAO is not null, then the service funtion checks if the password is correct for that particular customer ID or not. If the password is correct then the service function returns the customer bean or returns null. | Shubham | 2020-04-20 | 1 hr | 0.5 hrs | Completed | 1 hrs
|  | 5 | The Login Rest Controller invokes Service method and returns an encrypted customer ID as a response to the webService | Shubham | 2020-04-21 | 2 hrs | 0.5 hrs | Completed | 2 hrs
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| USBanking:011 | 1 | Wireframes and story boarding for each task | Shubham | 2020-04-23 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 2 | Routing Url List | Rohita | 2020-04-23 | 2 hrs | 1 hr | Completed | 1 hr
|  | 3 | Data classes details | Madhu | 2020-04-23 | 2 hrs | 0.2 hrs | Completed | 1.8 hrs
|  | 4 | Angular service | Megha | 2020-04-23 | 2.5 hrs | 0.5 hrs | completed | 2 hrs
|  | 5 | Components details | Yogesh | 2020-04-23 | 2 hrs | 0.5 hrs | completed | 1.5 hrs
|  | 6 | Detail about the security | Shubham | 2020-04-23 | 2 hrs | 0.3 hrs | completed | 1.7 hrs
| USBanking:012 | 1 | Test Plan Add Customer | Madhu | 2020-04-24 | 2 hrs | 0.5 hrs | completed | 1.5 hrs
|  | 2 | Test Plan for Add Account | Madhu | 2020-04-24 | 2 hrs | 0.5 hrs | completed | 1.5 hrs
|  | 3 | Test Plan for view accounts | Yogesh | 2020-04-24 | 3 hrs | 0.4 hrs | completed | 2.6 hrs
|  | 4 | Test Plan for view transactions | Megha | 2020-04-24 | 2 hrs | 0.2 hrs | completed | 1.8 hrs
|  | 5 | Test Plan for view transactions with date range | Megha | 2020-04-24 | 2 hrs | 0.5 hrs | completed | 1.5 hrs
|  | 6 | Test Plan for transfer funds | Rohita | 2020-04-24 | 3 hrs | 0.3 hrs | completed | 2.7 hrs
|  | 7 | Test Plan for login | Shubham | 2020-04-24 | 3 hrs | 0.5 hrs | completed | 2.5 hrs
| USBanking:013 | 1 | Bootstrapping angular application | Yogesh | 2020-04-24 | 2 hrs | 0 hrs | completed | 2 hrs
| USBanking:014 | 1 | Designing menu in template | Shubham | 2020-04-24 | 2 hrs | 0.3 hrs | Completed | 1.7 hrs
|  | 2 | Adding Routing details | Madhu | 2020-04-24 | 2 hrs | 0.2 hrs | Completed | 1.8 hrs
|  | 3 | Displaying standard info or advertisement | Yogesh | 2020-04-24 | 2 hrs | 0.2 hrs | Completed | 1.8 hrs
| USBanking:015 | 1 | Design a form that takes details of customer information | Madhu | 2020-04-25 | 3hrs | 0.5 hrs | Completed | 2.5 hrs
|  | 2 | Angular Component sends the details to angular service | Madhu | 2020-04-26 | 3 hrs | 0.2 hrs | Completed | 2.8 hrs
|  | 3 | Angular Service makes web service call and post the data gathered. | Madhu | 2020-04-27 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 4 | Common Validations | Madhu | 2020-04-27 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 5 | Business Validation for aadhar number and pan number | Yogesh | 2020-04-27 | 2.5 hrs | 0.5 hrs | Completed | 2 hrs
|  | 6 | Business Validation for customer number and minimum age should be 18 | Yogesh | 2020-04-28 | 3 hrs | 0.5 hrs | Completed | 2.5 hrs
| USBanking:016 | 1 | Design a form that takes details of addding account information | Madhu | 2020-04-25 | 3hrs | 0.5 hrs | Completed | 2.5 hrs
|  | 2 | Angular Component sends the details to angular service | Madhu | 2020-04-26 | 3 hrs | 0.2 hrs | Completed | 2.8 hrs
|  | 3 | Angular Service makes web service call and post the data gathered. | Madhu | 2020-04-27 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 4 | Common Validations | Madhu | 2020-04-27 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
| USBanking:017 | 1 | Decrypting customerId from token stored in localStorage | Yogesh | 2020-04-25 | 1 hrs | 0.5 hrs | completed | 1 hrs
|  | 2 | Component Sends customerId to Angular Service layer | Yogesh | 2020-04-25 | 2.5 hrs | 0.5 hrs | completed | 2 hrs
|  | 3 | Service layer makes webservice call and gets list of accounts that the customer has. | Yogesh | 2020-04-26 | 1 hrs | 0.5 hrs | completed | 1 hrs
|  | 4 | Designing the web page to show all the accounts. | Yogesh | 2020-04-26 | 3 hrs | 1 hrs | completed | 2.5 hrs
|  | 5 | Search text box to search account according to its type like saving or current or salaried. | Yogesh | 2020-04-27 | 1.5 hrs | 0.5 hrs | completed | 1 hrs
| USBanking:018 | 1 | Design a transfer fund form that takes in Customer Account ID, Beneficiary Account ID and amount need to transfer. | Rohita | 2020-04-25 | 4 hrs | 0.5 hrs | Completed | 3.5 hrs
|  | 2 | Component sends the details to service | Rohita | 2020-04-26 | 3 hrs | 0.5 hrs | Completed | 2.5 hrs
|  | 3 | Angular service make the web service call and get the Customer Account Id and Beneficiary Accou nt Id reference from the backend. | Rohita | 2020-04-27 | 3 hrs | 0.5 hrs | Completed | 2.5 hrs
|  | 4 | Design a web page to transfer the funds from one account to another. | Rohita | 2020-04-28 | 4 hrs | 0.5 hrs | Completed | 3.8 hrs
| USBanking:019 | 1 | Design a form that takes in account number, from date and to date | Megha | 2020-04-25 | 4 hrs | 0.2 hrs | Completed | 3.8 hrs
|  | 2 | Component sends the details to service | Megha | 2020-04-26 | 3 hrs | 0.5 hrs | Completed | 2.5 hrs
|  | 3 | Angular service make the webservice call and get the Account Id ref from the backend | Megha | 2020-04-26 | 3 hrs | 0.5 hrs | Completed | 2.5 hrs
|  | 4 | Design a web design to display transaction details or error response sent by the server | Megha | 2020-04-27 | 3 hrs | 0.3 hrs | Completed | 2.7 hrs
| USBanking:020 | 1 | Design a login form that validates the login credentials such as ID and password | Shubham | 2020-04-25 | 3 hrs | 0.5hrs | Completed | 2.5 hrs
|  | 2 | Component sends login ID and Password Details to service | Shubham | 2020-04-26 | 2hrs | 0.7 hrs | Completed | 2 hrs
|  | 3 | Angular service make the webservice call and Matches the LoginId and password | Shubham | 2020-04-26 | 3hrs | 0.5hrs | Completed | 2hrs
|  | 4 | Design a web page that validates the login credentials such as ID and password | Shubham | 2020-04-27 | 3hrs | 0.5hrs | Completed | 2.5 hrs
| USBanking:021 | 1 | Create a webpage that show the details like Customer ID, Contact number etc of the User who is logged in | Shubham | 2020-04-27 | 3 hrs | 0.5hrs | Completed | 2 hrs
|  | 2 | Component retrieves data from the angular service | Shubham | 2020-04-27 | 1 hr | 0.5 hrs | Completed | 1 hr
|  | 3 | Angular service makes the web service call and retrieves all the data of a particular user from the spring boot application | Shubham | 2020-04-27 | 1 hr | 0.5 hr | Completed | 1 hr
|  | 4 | Design the webpage | Shubham | 2020-04-27 | 1 hr | 0.5 hr | Completed | 1 hr